## Sheet1
Reporting Bugs Found in Functional Testing Phase
[5 empty] | Project Name | The Test Titans
[5 empty] | Project Type | Testing
[5 empty] | Tester | Nazish Jehangir
[5 empty] | Reviewer | Masai School
[5 empty] | Date Started | 2024-12-16
[5 empty] | Date Ended | 2024-12-20
[5 empty] | Operating Sytem | Windows 10
[5 empty] | Browser | Chrome
Defect ID | Defect Description | Test Case ID | Steps to Reproduce | Date Raised | Reference | Detected By | Status | Fixed By | Date Closed | Severity | Priority
FS_BUG_01 FS_BUG_02 FS_BUG_03 | Cart (BAG on Myntra) is not accessible & so is afunctional. User can't add/remove or update the cart section. | FT_01 FT_02 FT_03 | 1. Navigate to a product page. 2. Click "Add to Cart/Wishlist". 3. For removing or updating the cart, it's not here to access. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High
FS_BUG_04 | Feature is accessible but isn't functional due to unability to login and adding products. | FT_04 | 1. Navigate to the homepage. 2. Click on the Wishlist icon. 3. To check functionality look for a product to add. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Major | Medium
FS_BUG_05 FS_BUG_06 | The button for user to Login or Signup is not accessible & so is afunctional. | FT_05 FT_06 | 1. Navigate to the login page. 2. If it is accessible enter valid details / credentials. 3. Click on the login. 4. Test similarly with invalid or wrong credentials. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High
FS_BUG_07 | The user profile icon is not at all accessible or functional & user can't logged-in or create accounts on the website. | FT_07 | 1. Go to website's homepage. 2. Click on the user profile icon. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Major | Medium
FS_BUG_08 FS_BUG_09 | Search bar can be accessed but entering a query doesn't shows any result. Filtering & sorting features are available but don't function. | FT_08 FT_09 | 1. Navigate to the homepage. 2. Put an item name in search. 3. Press Enter. 4. If it functions test it similarly with invalid queries as inputs. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High
FS_BUG_10 | Almost all the links on home page failed to respond. Click on any link doesn't redirect to their respective pages except some random ones | FT_10 | 1. Navigate to the homepage. 2. Try clicking on every link and clickable elements on home to ensure clickability. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High
Reporting Bugs Found in Usability Testing Phase
Defect ID | Defect Description | Test Case ID | Steps to Reproduce | Date Raised | Reference | Detected By | Status | Fixed By | Date Closed | Severity | Priority
US_BUG_01 | Clicking on a product doesn't redirect to product details. | UT_04 | 1. Go to product details page. 2. observe the image quality by moving cursor towards it. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High
US_BUG_02 | Clicking on the cart (BAG) doesn't redirect to the cart section so I couldn't check layout & design of that page. | UT_05 | 1. Navigate to the BAG/cart section from the homepage. 2. Observe the layout and overall design of the page. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High
US_BUG_03 | the layout and design are quite good and user friendly but almost every link, button or element present there is not clickable or accssible. | UT_06 | 1. Navigate to the website on android mobile devices. 2. Observe the interface, design, layout, visibility, etc. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Major | Medium
Reporting Bugs Found in Usability Testing Phase
Defect ID | Defect Description | Test Case ID | Steps to Reproduce | Date Raised | Reference | Detected By | Status | Fixed By | Date Closed | Severity | Priority
PS_BUG_01 | Response time of key actions couldn't be measure because of the functionality issues. | PT_05 | 1. Navigate to the homepage. 2. Try clicking on every link. | 2024-12-19 | Bug Video | Nazish Jehangir | Open | Masai School | Pending | Critical | High