## Sheet1 (2)
Test Execution Report for Usability Test Cases
Test Case ID | Scenario/Module ID | Test Case Title | Status | Execution Date | Tester Name | Defect Found | Comments
UT_01 | US_05 | User Login/Signup Form | Partially Passed | 2024-12-18 | Nazish Jehangir | NA | Good design but feature doesn't work.
UT_02 | US_01 | Homepage | Passed | 2024-12-18 | Nazish Jehangir | NA | Design's good
UT_03 | US_02 | Product Search | Partially Passed | 2024-12-18 | Nazish Jehangir | NA | Filtering options are there but doesn't work
UT_04 | US_03 | Product Details Page | Failed | 2024-12-18 | Nazish Jehangir | US_BUG_01 | Feature doesn't exist
UT_05 | US_04 | Shopping Cart | Failed | 2024-12-18 | Nazish Jehangir | US_BUG_02 | Feature doesn't exist. (cart is not accessbile)
UT_06 | US_06 | Mobile UI | Failed | 2024-12-18 | Nazish Jehangir | US_BUG_03 | Links aren't interactive
UT_07 | US_07 | Mobile UI | Passed | 2024-12-18 | Nazish Jehangir | NA | Website has good desgin overall.
UT_08 | US_08 | Overall Usability | Passed | 2024-12-18 | Nazish Jehangir | NA | Website is responsive.
UT_09 | US_09 | Navigation | Partially Passed | 2024-12-18 | Nazish Jehangir | NA | Navbar is visible but doesn't function.